## Mobile App Estimation
Time Estimation for Loan mobile application
Sr. No. | Tasks list | Hours
1 | Data structure & Design | 60
Data structure
Design
2 | Users Registration and login | 18
Splash Screen and Home Page
User Registration & login (Including SSN and mobile number verification)
Login with social media
Forgot Password
3 | Landing Page/Dashboard | 18
Current loan (if any)
Credit score
Notifications
Side menu drawer (Taken as different module below in this document)
Credit Monitoring
4 | Side menu drawer | 18
Dashboard/Home
My Profile (Taken as different module below in this document)
Accounts (Taken as different module below in this document)
Transacations (Taken as different module below in this document)
Referrals
FAQ's
Terms and Conditions (This will be based on the state laws)
Settings
Log out
5 | Current Loan details/apply for the loan(if there is no loan under process) | 42
Amount of the loan
Start date of the loan
Address/edit address (option of address to be changed for postal service purpose)
pay back date of the loan
Contract signed
account details in which loan amount was transferred using stripe
Account detail status using PLAID
Late fees (if amount is not before xyz date)
Raise request to apply for loan
Option to share/Receive the contract to be signed against the loan
6 | My Profile | 18
Personal details like name, address, contact number etc.
Recent activities
7 | Accounts | 32
List of the accounts synced in the app
Account to be registered for transfer of loan
cash transfer using bank account
Implementing PLAID API to provide user the full detail of bank account
8 | Transactions | 20
History of all the transactions done through app
option to check the status of each transcation
option to share the transaction details
option to raise the ticket against each transcation
9 | Web services for mobile application | 90
| Total hrs for Mobile App | 316
Sr. No. | Admin Panel Tasks list | Hours
1 | Design, Data structure | 12
| Database schema definition and design | 12
2 | Users Registration and login | 4
User Login
Forgot Password
3 | Dashboard | 42
Bankroll information inlcluding : 1. Loans outstanding 2. Total customers 3. New customers 4. Weekly/monthly/annual growth etc. 5. List of upcming payments 6. Remaining balance.
User details page : 1. User personal info 2. User account details pulled from PLAID API 3. Status of current and past loans
5 | Loan criteria setup page | 42
Option to edit the dynamic/automated loan criteria
Option to configure the payment schedule through automated algorithm
Allow user to configure email settings
Print Notes
4 | Notifications | 24
Mass notification- Sends a push notification to all users
Selective Notification-Allows for sending out to specific users from backend
5 | Reports | 54
Summary of personal loan through payment history
Ability to export loan information and communicate with particular vendors
Export-Export selective information as a CSV
Mass Import-Allows for mass uploading of information based upon standard fields we set
Print Notes
6 | Managing permissions | 24
Allows admin to change what features can be used by individuals
Allows Admin to set up different users for different abilities
7 | Web Services for the admin panel | 90
| System Testing & Deployment | 80
System integration & testing
Bug Fixing
Regression Testing
Deployment
| Total for Admin panel | 372
| Grand Total for Mobile App(android app and iOS app) + admin panel + design + web services | 372+316=688